## Charter
Project Charter - Pipe Flow & Pump Sizing Calculator
Project lead: Lucas Cerriku ¦ Planned duration: Oct. 12 - Nov. 8, 2026 (4 weeks)
Objective | Build and validate a Python tool that calculates pressure drop, head loss and required pump power for single-phase pipe flow, and use it to compare pipe sizes for water and light crude oil.
In scope | Darcy-Weisbach pressure drop; laminar and turbulent (Colebrook-White) friction factor; minor fitting losses; elevation change; pump power; water (CoolProp) and light crude (user-defined) properties; scenario study and charts.
Out of scope | Multiphase flow, pipe networks, transient effects (water hammer), heat transfer, compressible gas flow.
Deliverables | 1) pipe_flow_calculator.py 2) Validation results 3) 40-scenario results table (CSV) 4) Two engineering charts 5) README / write-up 6) This project plan (charter, schedule, risk register, effort budget).
Success criteria | Laminar case returns f = 64/Re exactly; Colebrook agrees with Swamee-Jain within 3%; hand-calculated test case matches within 1%; all 40 scenarios run without error; finished within the 40-hour effort budget.
Constraints | About 10 hours per week alongside full-time studies, part-time work and varsity racing; free/open-source tools only ($0 budget).
Assumptions | Steady, incompressible, fully developed flow; commercial steel roughness 0.045 mm; light crude rho = 850 kg/m^3, mu = 0.005 Pa*s (typical values, replaceable with lab data); pump efficiency 75%.
Stakeholders | Project lead (self); peer / instructor reviewer for the validation results; target audience: engineering recruiters.

## Schedule
Schedule & Gantt Chart
Blue cells are inputs: edit Start, End, Status and % Complete as you go. Bars update automatically.
[8 empty] | Oct. 2026 | [19 empty] | Nov. 2026
WBS | Task | Phase | Start | End | Days | Status | % Done | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08
1.1 | Define scope, objectives & success criteria | Initiation | 2026-10-12 | 2026-10-13 | 2 | Not started | 0%
1.2 | Write project charter & risk register | Initiation | 2026-10-13 | 2026-10-14 | 2 | Not started | 0%
2.1 | Review Darcy-Weisbach, Colebrook & minor losses | Research | 2026-10-15 | 2026-10-18 | 4 | Not started | 0%
2.2 | Gather fluid property & pipe roughness data | Research | 2026-10-17 | 2026-10-19 | 3 | Not started | 0%
3.1 | Code fluid property module (CoolProp) | Development | 2026-10-20 | 2026-10-22 | 3 | Not started | 0%
3.2 | Code friction factor solver (laminar/Colebrook) | Development | 2026-10-22 | 2026-10-25 | 4 | Not started | 0%
3.3 | Code pressure drop & pump power functions | Development | 2026-10-26 | 2026-10-28 | 3 | Not started | 0%
4.1 | Validate vs hand calc, 64/Re and Swamee-Jain | Testing | 2026-10-29 | 2026-11-01 | 4 | Not started | 0%
5.1 | Run 40-scenario study & build charts | Analysis | 2026-11-02 | 2026-11-04 | 3 | Not started | 0%
6.1 | Write README & results summary | Closeout | 2026-11-05 | 2026-11-07 | 3 | Not started | 0%
6.2 | Lessons learned & final review | Closeout | 2026-11-08 | 2026-11-08 | 1 | Not started | 0%
| Total planned duration (days) |  |  |  | 28
| Overall % complete (average) | [5 empty] | 0%
Legend: blue bar = planned, green bar = task marked Complete

## Risk Register
Risk Register
Likelihood and Impact scored 1 (low) to 5 (high). Score = Likelihood x Impact; High >= 15, Medium >= 8.
ID | Risk | Category | Likelihood | Impact | Score | Rating | Mitigation | Status
R1 | Unit conversion error gives wrong results | Technical | 3 | 5 | 15 | High | Use SI units throughout; validate against a hand-calculated textbook case before running scenarios. | Open
R2 | Schedule slip from coursework, work and racing | Schedule | 4 | 3 | 12 | Medium | Plan ~10 h/week with weekend buffer; weekly progress check against the Gantt chart. | Open
R3 | Scope creep (pipe networks, multiphase flow) | Scope | 3 | 3 | 9 | Medium | Fixed scope in charter; log extra ideas in a 'future work' list instead of building them. | Open
R4 | Crude oil property data inaccurate | Data | 3 | 3 | 9 | Medium | Use typical published values, state them as assumptions, and let users enter lab data. | Open
R5 | Transitional flow (Re 2300-4000) less accurate | Technical | 3 | 2 | 6 | Low | Flag regime in every output; use Colebrook as a conservative estimate. | Open
R6 | Colebrook iteration fails to converge | Technical | 2 | 4 | 8 | Medium | Start from Swamee-Jain estimate; set tolerance and iteration cap. | Open
R7 | CoolProp fails to install | Tools | 2 | 2 | 4 | Low | Built-in water property correlations as fallback. | Open

## Effort Budget
Effort & Cost Budget
Enter actual hours in the blue column as you work. Software cost is $0 (Python, CoolProp, Matplotlib are free).
Phase | Planned hours | Actual hours | Variance (h) | Variance %
Initiation | 3
Research | 6
Development | 15
Testing | 6
Analysis | 5
Closeout | 5
Total | 40 | 0